## Cover
Project Challenge 2
Team 2
| Team Member : | 1 | Pyae Phyo Hein
|  | 2 | Khin Hnin Hsu
|  | 3 | Myat Kaung Khant
|  | 4 | Khin Kaung San Thu Tun
|  | 5 | Thant Htein Linn
|  |  |  | Create Date | 2022-06-01 00:03
|  |  |  | Update Date | 2022-06-01 00:03

## Customer Requirement
Customer Requirement (要件定義) | Yadanar Thike |  |  |  |  | Create Date | 2022-05-17
[6 empty] | Update Date | 2022-05-17
Customer Requirement
| 1 | Onine Book Shoping
|  | 1-1 | Admin Page (Login)
|  |  | 1-1-1 | Admin Page Inculde
|  |  |  | a) | Login/Out
|  |  |  | b) | Dashboard (Total Viewer,Total Reg User,Total Download,Order & Sale,...)
|  |  |  | c) | Book Info
- Add Item (Book=>Image,name,price,preview,stock,category,upload pdf,link generate)
- BookList /Update/Delete
|  |  |  | d) | Author Info
- Author List
- Author Add/Update/Delete
|  |  |  | e) | Shop Info -(Minior)
- Add/Update/Delete
|  |  |  | f) | Community
- Review & Rating(View)
- View From Contact Us
|  |  |  | g) | Order Info
- Today Order
- Order Detail Table (userinfo)
|  |  |  | h) | User Info
- view
|  |  |  | i) | Admin Setting
- Category Add/Update/Delete
- Logo Change
- favicon Change
- Slider Change
- Welcome Text
- Website info (phone,address,email,...)
- Guide Change
- Service Change
- PP Change
- FAQ Add/Update
- Generate Redemm Code -(Minior)
- Delivery Control -(Minior)
|  | 2-1 | Customer Home Page
|  |  | 2-1-1 | Customer Page Inculde
|  |  |  | a) | Login/Sign Up
|  |  |  | b) | User Profile
|  |  |  | c) | Order History
|  |  |  | d) | Add To Cart/Show Cart/CheckOut
|  |  |  | e) | Show Book View
|  |  |  | f) | Review & Rating
|  |  |  | g) | Free Download -(Minior)
|  |  |  | h) | View By Category
|  |  |  | i) | Search (Category,Author,Book Name)
|  |  |  | j) | Author Profile (Name,photo,count of book,...)
|  |  |  | k) | Shop List (popular shop by only Yangon State) -(Minior)
|  |  |  | m) | Guide of website
|  |  |  | n) | FAQ,Contact Us(From),Service,PP

## Schedule
Schedule (進捗） |  | Yadanar Thike | [9 empty] | Create Date | 2022-05-17
[12 empty] | Update Date | 2022-05-17
\
No | Sub | Task | Assign | Est Start | Est End | Duration Day | Act Start | Act End | Act Duration | Work Done
1 |  | Schedule（進捗） | All | 2022-05-17 | 2022-06-03 | 17 | 2022-05-17 |  | -44698
2 |  | Project Flow（流れ） | MKK | 2022-05-17 | 2022-05-20 | 3 | 2022-05-17 | 2022-05-18 | 1 | 90%
3 |  | Screen Design（画面設計） | All | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-22 | 5 | 90%
| 1 | Login | PPH | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-18 | 1 | 90% | Admin
| 2 | Dashboard | PPH | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-18 | 1 | 90%
| 3 | Author list | PPH | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-18 | 1 | 90%
| 4 | Author Add | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-18 | 1 | 90%
| 5 | Book list | PPH | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-18 | 1 | 90%
| 6 | Book Add | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-18 | 1 | 90%
| 7 | Order Info | PPH | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 8 | User Info | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 9 | Admin Settings | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 10 | Home Screen | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 11 | Categories List | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 12 | Categories Add | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 13 | Contact Edit | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 14 | Add Admin | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 15 | Privacy & policy list | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 16 | Delivery control list | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 17 | Service list | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 18 | Guide list | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 19 | Guide add | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 20 | Privacy & policy add | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 21 | Delivery Control add | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 22 | Service add | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 23 | FAQ list | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 24 | FAQ add | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 25 | Contact | PPH | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 26 | Review | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 27 | Slide change list | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 28 | Slide change add | MKK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 1 | User_Login | KK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-18 | 1 | 90% | customer
| 2 | User_Register | KK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-18 | 1 | 90%
| 3 | Home | KHH | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 4 | Book Description | KK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 5 | Author Profile | KHH | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-20 | 3 | 90%
| 6 | Author List | KHH | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-20 | 3 | 90%
| 7 | Book Categories | KK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 8 | Order Page | KK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-20 | 3 | 90%
| 9 | Contact Us | THL | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-18 | 1 | 90%
| 10 | Service | THL | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 11 | Privacy & Policy | THL | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-19 | 2 | 90%
| 12 | User setting | KK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-21 | 4 | 90%
| 13 | Order History | KK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-21 | 4 | 90%
| 14 | FAQ | THL | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-18 | 1 | 90%
| 15 | Cart pop-up | KK | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-20 | 3 | 90%
| 16 | Shop List | KHH | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-22 | 5 | 90%
| 17 | Delivery Contrtol | KHH | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-22 | 5 | 90%
| 18 | Guide | THL | 2022-05-17 | 2022-05-22 | 5 | 2022-05-17 | 2022-05-22 | 5 | 90%
4 |  | Database（DB設計書） | KK | 2022-05-20 | 2022-05-23 | 3 | 2022-05-21 | 2022-05-22 | 1 | 90%
5 |  | Development（開発） | All | 2022-05-23 | 2022-06-02 | 10 |  |  | 0
| 1 | Login | PPH | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 2 | Dashboard | PPH | 2022-05-23 | 2022-05-24 | 1 |  |  | 0
| 3 | Author list | PPH | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 4 | Author Add | PPH | 2022-05-25 | 2022-05-26 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 5 | Book list | PPH | 2022-05-25 | 2022-05-26 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 6 | Book Add | PPH | 2022-05-25 | 2022-05-26 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 7 | Order Info | PPH | 2022-05-27 | 2022-05-28 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 8 | User Info | PPH | 2022-05-27 | 2022-05-28 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 9 | Admin Settings | PPH | 2022-05-27 | 2022-05-28 | 1 |  |  | 0
| 10 | Home Screen | PPH | 2022-05-29 | 2022-05-30 | 1 | 2022-05-27 | 2022-05-28 | 1 | 50%
| 11 | Categories List | PPH | 2022-05-29 | 2022-05-30 | 1 |  |  | 0
| 12 | Categories Add | PPH | 2022-05-29 | 2022-05-30 | 1 | 2022-05-25 | 2022-05-26 | 1 | 50%
| 13 | Contact Edit | MKK | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 14 | Add Admin | MKK | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 15 | Privacy & policy list | MKK | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 16 | Delivery control list | MKK | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 17 | Service list | MKK | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 18 | Guide list | MKK | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 19 | Guide add | MKK | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 20 | Privacy & policy add | MKK | 2022-05-24 | 2022-05-25 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 21 | Delivery Control add | MKK | 2022-05-24 | 2022-05-25 | 1 | 2022-05-24 | 2022-05-25 | 1 | 50%
| 22 | Service add | MKK | 2022-05-24 | 2022-05-25 | 1 | 2022-05-24 | 2022-05-25 | 1 | 50%
| 23 | FAQ list | MKK | 2022-05-24 | 2022-05-25 | 1 | 2022-05-24 | 2022-05-25 | 1 | 50%
| 24 | FAQ add | MKK | 2022-05-24 | 2022-05-25 | 1 | 2022-05-24 | 2022-05-25 | 1 | 50%
| 25 | Contact | MKK | 2022-05-24 | 2022-05-25 | 1 | 2022-05-25 | 2022-05-26 | 1 | 50%
| 26 | Review | MKK | 2022-05-24 | 2022-05-25 | 1 | 2022-05-25 | 2022-05-26 | 1 | 50%
| 27 | Slide change list | MKK | 2022-05-24 | 2022-05-25 | 1 | 2022-05-25 | 2022-05-26 | 1 | 50%
| 28 | Slide change add | MKK | 2022-05-24 | 2022-05-25 | 1 | 2022-05-25 | 2022-05-26 | 1 | 50%
| 1 | User_Login | KK | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 2 | User_Register | KK | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 3 | Home | KHH | 2022-05-24 | 2022-05-25 | 1 | 2022-05-25 |  | -44706 | 20%
| 4 | Book Description | KK | 2022-05-24 | 2022-05-25 | 1 | 2022-05-24 | 2022-05-25 | 1 | 50%
| 5 | Author Profile | KHH | 2022-05-25 | 2022-05-26 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 6 | Author List | KHH | 2022-05-26 | 2022-05-27 | 1 | 2022-05-24 | 2022-05-25 | 1 | 50%
| 7 | Book Categories | KK | 2022-05-24 | 2022-05-25 | 1 | 2022-05-24 | 2022-05-25 | 1 | 50%
| 8 | Order Page | KK | 2022-05-25 | 2022-05-26 | 1 | 2022-05-24 | 2022-05-25 | 1 | 50%
| 9 | Contact Us | THL | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 10 | Service | THL | 2022-05-23 | 2022-05-24 | 1 | 2022-05-27 | 2022-05-28 | 1 | 50%
| 11 | Privacy & Policy | THL | 2022-05-23 | 2022-05-24 | 1 | 2022-05-23 | 2022-05-24 | 1 | 50%
| 12 | User setting | KK | 2022-05-25 | 2022-05-26 | 1 | 2022-05-25 | 2022-05-26 | 1 | 50%
| 13 | Order History | KK | 2022-05-25 | 2022-05-26 | 1 | 2022-05-25 | 2022-05-26 | 1 | 50%
| 14 | FAQ | THL | 2022-05-25 | 2022-05-26 | 1 | 2022-05-26 | 2022-05-27 | 1 | 50%
| 15 | Cart pop-up | KK | 2022-05-25 | 2022-05-26 | 1 | 2022-05-25 | 2022-05-26 | 1 | 50%
| 16 | Shop List | KHH | 2022-05-23 | 2022-05-24 | 1 | 2022-05-24 | 2022-05-25 | 1 | 50%
| 17 | Delivery Contrtol | KHH | 2022-05-23 | 2022-05-24 | 1 | 2022-05-24 | 2022-05-25 | 1 | 50%
| 18 | Guide | THL | 2022-05-24 | 2022-05-25 | 1 | 2022-05-24 | 2022-05-25 | 1 | 50%
6 |  | Unit Test（単体試験） |  |  |  | 0 |  |  | 0
7 |  | Integration Test（結合試験） |  |  |  | 0 |  |  | 0
314
[5 empty] | Month | 10.4667

## By Person
Schedule (進捗） |  | Yadanar Thike | [15 empty] | Create Date | 2022-05-17
[18 empty] | Update Date | 2022-05-17
No | Name | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
1 | Pyae Phyo Hein | 17: Screen Design; 23: Login,Dashboard,Author list,Author Add,Book list,Book Add,Order Info,User Info,Admin Settings,Home Screen,Categories List,Categories Add
2 | Khin Hnin Hsu | 17: Screen Design; 23: Home,Author Profile,Author List,Shop List,Delivery Contrtol
3 | Myat Kaung Khant | 17: Project Flow; 19: Screen Design; 23: Contact Edit,Add Admin,Privacy & policy list,Delivery control list,Service list,Guide list,Guide add,Privacy & policy add,Delivery Control add,Service add,FAQ list,FAQ add,Contact,Review,Slide change list,Slide change add
4 | Khin Kaung San Thu Tun | 17: Screen Design; 20: DB Design; 24: User_Login,User_Register,Book Description,Book Categories,Order Page,User setting,Order History,Cart pop-up; 27: Home page Navigation adjust; 29: Frontend development design fixing
5 | Thet Htein Lin | 17: Screen Design; 23: Contact Us,Service,Privacy & Policy,FAQ,Guide

## Main Flow
Main Flow (プロジャック流れ） |  | Yadanar Thike |  |  |  |  | Create Date | 2022-05-17
[7 empty] | Update Date | 2022-05-17
Explanation of Project
プロジャックの説明
(プロジャック流れ）
| Path： | Admin |  |  | Path： | User
No
Yes
No
Yes
Start
Register
User Panal
Have account?
Login
Admin Panel
Dashboard
Author Info
Book Info
Order Info
Community
Add Items
Book List
Author List
Add
Update
Delete
User Info
Admin Setting
Total Viewer
Total Reg User
Order & Sales
Review & Rating
View from contacts
Today Order
Order Detail Table
View
-user name
-phone no
-address
-email
- Category Add/Update/Delete
- Logo Change
- favicon Change
- Slider Change
- Welcome Text
- Website info (phone,address,email,...)
- Guide Change
- Service Change
- PP Change
- FAQ Add/Update
- Generate Redemm Code -(Minior)
- Delivery Control -(Minior)
Start
Home
Categories
Search Box
Author
Login/Reg
Books View
Categories Lists
Authors Lists
by Category
by Author
by Name
Click Book
Book Description
User Profile
Show Cart
Have Account?
Add to Cart
Buy
Complete
Change Name
Change Phone No
Change Image
Review & Rating
Footer
Shop List
Delivery Control
Services
Policy & Pravicy
Shop by States
Cart
Order History
Change Address
Authors Details
Guide

## Screen Design
Screen Design (画面設計） | Yadanar Thike | [7 empty] | Create Date | 2022-05-17
[9 empty] | Update Date | 2022-05-17
Admin
Screen Name ： |  | Login | Screen Name ： |  | Dashboard |  | Screen Name ： |  | Author List
Screen Name ： |  | Author Add | Screen Name ： |  | Book List |  | Screen Name ： |  | Book Add
Screen Name ： |  | Order Info | Screen Name ： |  | User Info |  | Screen Name ： |  | Admin Settings
Screen Name ： |  | Home Screen | Screen Name ： |  | Categories List |  | Screen Name ： |  | Categories Add
Screen Name ： |  | Contact Edit | Screen Name ： |  | Add Admin |  | Screen Name ： |  | Slide Change List
Screen Name ： |  | Slide Change Add | Screen Name ： |  | Privacy&policy List |  | Screen Name ： |  | Privacy&policy Add
Screen Name ： |  | Guide List | Screen Name ： |  | Guide Add |  | Screen Name ： |  | DeliveryControl List
Screen Name ： |  | DeliveryControl Add | Screen Name ： |  | Service List |  | Screen Name ： |  | Service Add
Screen Name ： |  | FAQ List | Screen Name ： |  | FAQ Add |  | Screen Name ： |  | Review&Rating
Screen Name ： |  | Contact
Customer
Screen Name ： |  | Login |  | Screen Name ： |  | Register |  | Screen Name ： |  | Home

## DB Design
DB Design (DB設計） |  | Yadanar Thike | [8 empty] | Create Date | 2022-05-17
[11 empty] | Update Date | 2022-05-21
| DB Name ： |  | YadanarThike_DB
| Table Name ： |  | Book_M
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | book_id | Book's id | - | - | Y | INT | 11
| 3 | book_name | Book's name | - | - | Y | VARCHAR | 256
| 4 | book_price | Book's price | - | - | Y | INT | 11
| 5 | author_id | Book's author | - | - | Y | INT | 11
| 6 | view count |  | - | - | - | INT | 11
| 7 | book_desp | Book's decription | - | - | - | VARCHAR | 1024
| 8 | category_id | Book's category | - | - | Y | INT | 11
| 9 | publisher_id | Book's publisher | - | - | Y | INT | 11
| 10 | page_number | Book's page number | - | - | Y | INT | 11
| 11 | size | Book's size | - | - | Y | VARCHAR | 256
| 12 | book_img | Book's img | - | - | Y | VARCHAR | 256
| 13 | stock_number | Book's current stock number | - | - | Y | INT | 11
| 14 | book_pdf | Book's pdf | - | - | - | VARCHAR | 256
| 15 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 16 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 17 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 18 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 19 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | Author
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | author_id | Author's id | - | - | Y | INT | 11
| 3 | author_name | Author's name | - | - | Y | VARCHAR | 256
| 4 | author_name_category | For the same name character for the author | - | - | Y | VARCHAR | 6
| 5 | author_about | Author's about | - | - | - | VARCHAR | 1024
| 6 | author_life | Author's life | - | - | - | VARCHAR | 128
| 7 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 8 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 9 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 10 | updated_date | Date this table was updated | - | - | - | VARCHAR | 10
| 11 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | Category
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | category_id | category's id | - | - | Y | INT | 11
| 3 | category_name | category name | - | - | Y | VARCHAR | 256
| 4 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 5 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 6 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 7 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 8 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | Publisher
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | publisher_id | publisher's id | - |  | Y | INT | 11
| 3 | publisher_name | publisher's name | - | - | Y | VARCHAR | 256
| 4 | book_id | Book that was published by this publisher | - | - | Y | INT | 11
| 5 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 6 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 7 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 8 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 9 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | Review_rating
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | review_id | review's id | - | - | Y | INT | 11
| 3 | book_id | book's id | - | - | Y | INT | 11
| 4 | customer_id | Customer's id | - | - | Y | INT | 11
| 5 | comment | Reviewer's comment | - | - | Y | VARCHAR | 256
| 6 | review_date | Date that the user written about that book | - | - | Y | VARCHAR | 256
| 7 | rating | User's rating for the book | - | - | Y | INT | 11 |  | 1 to 5 , 1 will be one star
| 8 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 9 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 10 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 11 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 12 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | Customer
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | customer_id | customer's id | - | - | Y | INT | 11
| 3 | customer_name | customer's name | - | - | Y | VARCHAR | 256
| 4 | customer_phno | customer's phno | - | - | Y | VARCHAR | 20
| 5 | customer_email | customer's email | - | - | Y | VARCHAR | 256
| 6 | customer_password | customer's pass | - | - | Y | VARCHAR | 128
| 7 | customer_profileImg | customer's profileImg | - | - | - | VARCHAR | 256
| 8 | valid | user? Ban? | - | - | Y | INT | 11 |  | 0:valid 1:ban
| 9 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 10 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 11 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 12 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 13 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | Order
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | order_id | order's id | - | - | Y | INT | 11
| 3 | customer_id | customer's table id | - | - | Y | INT | 11
| 4 | book_id | Book' table id | - | - | Y | INT | 11
| 5 | customer_division | Division or State of the customer | - | - | Y | VARCHAR | 256
| 6 | customer_town | Town of the customer | - | - | Y | VARCHAR | 256
| 7 | customer_address | Address of the cutomer | - | - | Y | VARCHAR | 256
| 8 | total_price | Total cost for one order | - | - | Y | INT | 11
| 9 | delivery_id | Delivery fee of the order | - | - | Y | INT | 11
| 10 | order_quantity | the number book per order | - | - | Y | INT | 11
| 11 | order_status | pending?complete?- | - | - | - | INT | 11 |  | 0:Pending 1:Complete
| 12 | order_date | the date that user ordered | - | - | Y | VARCHAR | 10
| 13 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 14 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 15 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 16 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 17 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | Login
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | login_id | customer's id | - | - | Y | INT | 11
| 3 | customer_id | customer's id | - | - | Y | INT | 11
| 4 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 5 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 6 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 7 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 8 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | Card_item
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | card_item_id | card item's id | - | - | Y | INT | 11
| 3 | book_id | book's id | - | - | Y | VARCHAR | 256
| 4 | item_quantity | book's quantity | - | - | Y | INT | 11
| 5 | total_price | total price of book in the card | - | - | Y | INT | 11
| 6 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 7 | created_date | Date this table was created | - | - | Y | INT | 11
| 8 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 9 | updated_date | Date this table was updated | - | - | - | INT | 11
| 10 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | delivery
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | delivery_id | delivery's id | - | - | Y | INT | 11
| 3 | state_id | state's id | - | - | Y | VARCHAR | 256
| 4 | township_id | township's id | - | - | Y | VARCHAR | 256
| 5 | delivery_fee | one line deli fee | - | - | Y | INT | 11
| 6 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 7 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 8 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 9 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 10 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | state
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | state_id | state's id | - | - | Y | INT | 11
| 3 | state_name | state and division's name | - | - | Y | VARCHAR | 256
| 4 | delivery_id |  | - | - | Y | INT | 11
| 5 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 6 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 7 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 8 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 9 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | township
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | township_id | township's id | - | - | Y | INT | 11
| 3 | township_name | township's name | - | - | Y | VARCHAR | 256
| 4 | delivery_id |  | - | - | Y | INT | 11
| 5 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 6 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 7 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 8 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 9 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | FAQ
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | faq_id | FAQ's id | - | - | Y | INT | 11
| 3 | question |  | - | - | Y | VARCHAR | 256
| 4 | answer |  | - | - | Y | VARCHAR | 256
| 5 | order | order's id | - | - | Y | INT | 11
| 6 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 7 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 8 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 9 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 10 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | Admin
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | admin_id | admin's id | - | - | Y | INT | 11
| 3 | admin_name | admin's name | - | - | Y | VARCHAR | 256
| 4 | admin_password | admin's password | - | - | Y | VARCHAR | 256
| 5 | Role | admin's role | - | - | Y | INT | 11 |  | 0:SA 1:NA
| 6 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 7 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 8 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 9 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 10 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | Privacy&policy
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | pp_id | Privacy and policys' id | - | - | Y | INT | 11
| 3 | question |  | - | - | Y | VARCHAR | 256
| 4 | answer |  | - | - | Y | VARCHAR | 256
| 5 | order | order's id | - | - | Y | INT | 11
| 6 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 7 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 8 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 9 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 10 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | Service
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | service_id | Service's id | - | - | Y | INT | 11
| 3 | question |  | - | - | Y | VARCHAR | 256
| 4 | answer |  | - | - | Y | VARCHAR | 256
| 5 | order | order's id | - | - | Y | INT | 11
| 6 | icon | service's icon | - | - | Y | VARCHAR | 256
| 7 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 8 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 9 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 10 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 11 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | Site_master
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | name | shop's name | - | - | Y | VARCHAR | 256
| 3 | logo | shop's Logo | - | - | Y | VARCHAR | 256
| 4 | icon | shop's icon | - | - | Y | VARCHAR | 256
| 5 | phone | shop's phno | - | - | Y | VARCHAR | 20
| 6 | address | shop's address | - | - | Y | VARCHAR | 256
| 7 | email | shop's email | - | - | Y | VARCHAR | 256
| 8 | slider_1 | shop's slider | - | - | Y | VARCHAR | 256
| 9 | slider_2 | shop's slider | - | - | Y | VARCHAR | 256
| 10 | welcome_text | shop's wel_txt | - | - | Y | VARCHAR | 256
| 11 | available_time | Open_time & Close_time | - | - | Y | VARCHAR | 256
| 12 | facebook | shop's facebook | - | - | Y | VARCHAR | 256
| 13 | instagram | shop's instagram | - | - | Y | VARCHAR | 256
| 14 | twitter | shop's twitter | - | - | Y | VARCHAR | 256
| 15 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 16 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 17 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 18 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 19 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | shop list
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | shop_id | shop's id |  | - | Y | INT | 11
| 3 | shop_Cate | shop's categories | - | - | Y | VARCHAR | 256
| 4 | shop_name | shop's name | - | - | Y | VARCHAR | 256
| 5 | address | shop's address | - | - | Y | VARCHAR | 256
| 6 | state_id | state's id | - | - | Y | INT | 11
| 7 | township_id | township's id | - | - | Y | INT | 11
| 8 | phone no | shop's phone | - | - | Y | VARCHAR | 20
| 9 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 10 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 11 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 12 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 13 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | user_guide
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | userguide_id | userguide's id | - | - | Y | INT | 11
| 3 | userguide_title | the title of the userguide | - | - | Y | VARCHAR | 256
| 4 | userguide_text | userguide text | - | - | Y | VARCHAR | 1024
| 5 | order_id |  | - | - | Y | INT | 11
| 6 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 7 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 8 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 9 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 10 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256
| Table Name ： |  | slider
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Table's id | Y | Y | Y | INT | 11
| 2 | slider_id | slide's id | - | - | Y | INT | 11
| 3 | slider_image | slide image | - | - | Y | VARCHAR | 256
| 4 | del_flg | Delete flag | - | - | Y | INT | 11 |  | 0:Exist 1:Delete
| 5 | created_date | Date this table was created | - | - | Y | VARCHAR | 10
| 6 | created_by | Name this table was created | - | - | Y | VARCHAR | 256
| 7 | updated_date | Date this table was updated | - | - | - | VARCHAR | 11
| 8 | updated_by | Name this table was updated | - | - | - | VARCHAR | 256